## Sheet1
For 24 Lake Ave, Oyster Bay, NY
# | Budget Item | Description | Amount | Timeline
20101 | Plans
20102 | Permits
10101 | Site Prep
10102 | Demo |  | 15000 | 60 days
10103 | Dumpsters |  | 3000 | 30 days
20102 | Survey
10104 | Septic
10105 | Foundation
10106 | Plumbing - Rough |  | 12000 | 120 days
10107 | Plumbing-Finish | fixtures | 3000 | 120 days
10108 | Framing
10109 | Electric -Rough |  | 13000 | 120 days
10110 | Electrical-Finish | fixtures | 3000 | 120 days
10111 | HVAC
10112 | Furnace |  | 15000 | 160 days
10113 | Water Heater |  | 2000 | 160 days
10114 | Air conditioner |  | 2000 | 160 days
10115 | Fireplace
10116 | Roof |  | 30000 | 90 days
10117 | Insulation |  | 3000 | 160 days
10118 | Drywall | Materials- $5000 Labor- $3000 | 8000 | 160 days
10119 | Paint - Interior |  | 3500 | 180 days
10120 | Paint - Exterior
10121 | Windows |  | 13500 | 90 days
10122 | Siding |  | 18000 | 90 days
10123 | Gutters
10124 | Doors - Interior |  | 1500 | 210 days
10125 | Doors - Exterior |  | 1500 | 210 days
10126 | Door - Garage
10127 | Door - Closet
10128 | Molding/Trim |  | 2000 | 210 days
10129 | Cabinets - Kitchen |  | 15000 | 240 days
10130 | Cabinets - Bathroom |  | 3500 | 240 days
10131 | Countertops - Kitchen |  | 3000 | 240 days
10132 | Countertops - Bathroom |  | 800 | 240 days
10133 | Chimney
10134 | Masonry
10135 | Flooring - Tile | Kitchen- $2500 Bathroom- $500 Tile- $2000 | 5000 | 240 days
10136 | Flooring - Hardwood |  | 15000 | 240 days
10137 | Flooring - Carpet
10138 | Flooring - Laminate
10139 | Appliance - Refrigerator |  | 1000 | 240 days
10140 | Appliance - Stove |  | 1000 | 240 days
10141 | Appliance - Oven
10142 | Appliance - Other | Diswasher, Washer and Dryer | 3000 | 240 days
10143 | Driveway
10144 | Decking / Patio | Front Deck 2000 Back Deck 4000 | 6000 | 270 days
10145 | Landscaping |  | 2000 | 270 days
10146 | Fencing
10147 | Sink - Kitchen |  | 1000 | 240 days
10148 | Sink - Bathroom |  | 500 | 240 days
10149 | Cabinet Hardware |  | 2000 | 240 days
10150 | Bath Tub |  | 1800 | 240 days
10151 | Vanity Mirror |  | 900 | 240 days
10152 | Shower
10153 | Tile |  | 2000 | 240 days
10154 | Toilet |  | 800 | 240 days
10155 | Closet Shelving
10156 | Stucco
10157 | Stairs |  | 3000 | 180 days
10158 | Soffit/Facia
10159 | Door Bell
10160 | Pool
10161 | Ceiling Fan
10162 | Final Clean |  | 1000 | 270 days
10163 | Staging
20103 | Contingency
10164 | Mold Remediation
20104 | Other
10169 | Other
10170 | Other
|  | TOTAL | 217300

## draw
Budget Item | Description | Amount | Timeline | Draw Schedule
Dumpsters |  |  | 30 days
Demo |  |  | 60 days
Roof |  |  | 90 days
Windows |  |  | 90 days
Siding |  |  | 90 days
Plumbing - Rough |  |  | 120 days
Plumbing-Finish |  |  | 120 days
Electric -Rough |  |  | 120 days
Electrical-Finish |  |  | 120 days
Furnace |  |  | 160 days
Water Heater |  |  | 160 days
Air conditioner |  |  | 160 days
Insulation |  |  | 160 days
Drywall |  |  | 160 days
Paint - Interior |  |  | 180 days
Stairs |  |  | 180 days
Doors - Interior |  |  | 210 days
Doors - Exterior |  |  | 210 days
Molding/Trim |  |  | 210 days
Cabinets - Kitchen |  |  | 240 days
Cabinets - Bathroom |  |  | 240 days
Countertops - Kitchen |  |  | 240 days
Countertops - Bathroom |  |  | 240 days
Flooring - Tile |  |  | 240 days
Flooring - Hardwood |  |  | 240 days
Appliance - Refrigerator |  |  | 240 days
Appliance - Stove |  |  | 240 days
Appliance - Other |  |  | 240 days
Sink - Kitchen |  |  | 240 days
Sink - Bathroom |  |  | 240 days
Cabinet Hardware |  |  | 240 days
Bath Tub |  |  | 240 days
Vanity Mirror |  |  | 240 days
Tile |  |  | 240 days
Toilet |  |  | 240 days
Decking / Patio |  |  | 270 days
Landscaping |  |  | 270 days
Final Clean |  |  | 270 days